## Homepage

- Could we add an overarching intro project summary/sentence at the very start?

  - Strengthening Pesticide Poisoning Surveillance and Response in South Africa
A policy package proposing an integrated, costed strategy to close the detection gap, coordinate health and agriculture responses, and restrict the most hazardous organophosphate pesticide (terbufos).

- “Table of Contents” style linking at the end of the page:

  - The Policy Brief Hub

  - The three individual policy briefs (Surveillance, Coordination, Terbufos)

  - The technical appendices (Decision Model, Costing Analysis, Surveillance Concept Note, Parameters Hub)

## Policy Brief Hub

- After the summaries of the three we could add an example “Package Summary”:

E.g. Total Package at a Glance

| Component | Near-Term Recommendation | Steady-State Annual Operating Cost | Expected Impact |
| --- | --- | --- | --- |
| Surveillance | MVP (Options 1+2) | ~R137,000 | Detection from <5% to ~19% of true cases |
| Coordination | Full Package | ~R145,000 | ~957 deaths averted/year at scale |
| Terbufos | T2 restriction with 24-month evaluation gate | (see Brief 3) | ≥50% reduction in attributable serious poisonings or automatic escalation to full ban |

Combined near-term operating cost: ~R282,000/year.

- Sentence summary above the “The three policy briefs”:

In brief: Invest ~R282,000/year in integrated surveillance and coordination infrastructure. Immediately tighten restrictions on terbufos with a 24-month review that triggers a full ban if attributable serious poisonings do not fall by a pre-agreed margin. Projected impact: ~957 deaths averted/year at scale.

- Expanding the “How the three briefs fir together” (adding this below the figure):

  - Why all three are necessary – and the risks of partial adoption

These briefs are not a menu of independent options. Each depends on the others to deliver its claimed impact:

  - Surveillance without coordination generates notifications that lead nowhere. Better detection will increase the visible case count; without a closed-loop investigation and referral workflow (Brief 2), the system will see more poisonings but respond to none of them – a politically damaging outcome.

  - Coordination without surveillance has nothing to coordinate. The closed-loop workflow requires a reliable signal to trigger investigation and source removal. At the current <5% detection rate, it would sit largely idle.

  - Regulatory restriction without coordination is unenforceable. A terbufos restriction or ban is a paper policy unless the compliance monitoring, source-removal trigger, and enforcement feedback loop (Brief 2) are operational. The street pesticide diversion pathway cannot be disrupted by regulation alone.

  - Coordination and surveillance without product-specific action lack a measurable first target. Terbufos, as the leading cause of severe OP mortality, is the concrete target that proves the system works and justifies further investment.

The recommendation is a single, integrated package. Adopting fewer than all three components will not achieve the projected impact and may actively create problems – more visible cases with no response mechanism, or a ban with no enforcement capacity. The phased implementation described in each brief builds the system in the required sequence, not as alternatives.

- We could include a “Cost of Inaction” after the “Total Package”:

Cost of inaction. The current system detects <5% of true pesticide poisonings, at an annual societal burden of ~R2.34 billion, of which ~R80 million falls directly on the public health budget. Every year of delay means continued preventable deaths and expenditure, against a proposed investment of ~R282,000/year – a 0.35% uplift on current health-system pesticide-related costs.

## Policy Brief 1: Strengthening Surveillance

- Cost of Inaction statement in opening:

E.g.: “The current surveillance system detects <5% of true poisonings. Every year at this detection rate, approximately [X] deaths go unrecorded and uninvestigated, and the evidence base for regulatory action remains weak.”

- Addition to Section 5, Option 4 (before the “Governance paragraph”):

Why Option 4 is essential. Without it, improved detection (Options 1 and 2) will generate more notifications that lead nowhere. The system will see more poisonings but respond to none – a politically damaging outcome that undermines sustained investment. Option 4 is the minimum investment to convert detection into investigation and source removal. At ~R45,000 setup and ~R35,000/year operating, it is the lowest-cost component of the package and the bridge that prevents the MVP investment from being wasted. It directly enables the Coordination brief.

- Adding to the introduction fir the recommended next step (section 9):

The MVD specifications in Appendix A should be formally adopted by NDoH as the data standard for all NMC pesticide notifications, PIH ingest, and NHLS auto-notifications. This ensures all three streams speak the same data language from the outset, enabling cross-stream linkage and agent-specific attribution.

- Add a row or footnote to the “Implementation considerations” table (in section 8):

Integrated surveillance dashboard: Housed at NICD, with access tiers: (a) internal line-list for NICD signal detection; (b) aggregate provincial/district dashboards for local response; (c) public-facing de-identified aggregate view for accountability and advocacy.

## Policy Brief 2: Coordination

- Cost of Inaction statement in opening:

E.g. “Without a closed-loop coordination mechanism, notifications lead nowhere. The R80 million/year the health system already spends on poisoning care is not leveraged to prevent future cases.”

- Could we clarify the org/institutional home for the workflow:

Institutional home. We recommend NICD be the coordinating hub for the closed-loop workflow. NICD already hosts the NMC platform that generates the initial notification, has epidemiological expertise, and existing relationships with provincial health and DALRRD. A dedicated coordination officer (0.5 FTE, included in the R145,000/year) would sit within NICD’s outbreak response or environmental health unit. NICD would maintain the workflow platform, track KPIs, manage the intelligence feed, and produce quarterly performance reports – but not conduct field investigations or enforcement (those remain with provincial EHPs and DALRRD).

- Including enforcement and accountability mechanisms to the full package description:

E.g.

- CIF completion within 48 hours and DALRRD referral closure within 30 days shall be district-level KPIs, reported quarterly on the joint dashboard.

- Quarterly performance reports shall go to the provincial Director-General, copied to the national DGs of Health and Agriculture.

- Persistent non-compliance (<70% completion for two consecutive quarters) triggers escalation to the provincial DG with a required remedial plan.

- The joint KPI dashboard shall be accessible to parliamentary portfolio committees on Health and Agriculture, creating political accountability. Aggregate, de-identified data shall be public.

- Including a “dependencies” and “limitations” additions to the full package description:

Dependencies:

- Input from Brief 1, Option 4: The structured CIF and agricultural extension module are required to provide standardised investigation data. Without them, the coordination workflow lacks consistent, actionable inputs.

- Output to Brief 3, T2 enforcement: The coordination system provides the source-removal trigger, joint compliance task force, and intelligence feed needed to enforce terbufos restrictions. T2 is conditional on this package being operational.

Limitations: It ensures every detected case triggers an investigation and, where indicated, a regulatory response. It does not: (a) increase detection (that’s Brief 1); (b) guarantee successful prosecution (depends on DALRRD capacity and evidentiary standards); or (c) address the root causes of intentional self-harm. It is a necessary, not sufficient, condition for effective governance.

## Appendix: “Implementation at a Glance” (suggestion for inclusion)

| Component | Recommendation | Lead Agency | Year 1 Cost | Steady-State Cost | Expected Impact | Timeline | Depends On |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Surveillance | Adopt MVP | NICD | R377,000 | R137,000 | P_detect 5%→19% | 12 weeks | – |
| Surveillance | Adopt Option 4 (CIF) | NDoH/NICD | R80,000 | R35,000 | Enables source removal | 4–8 weeks | MVP |
| Coordination | Adopt Full Package | NICD (hub), DALRRD (enforcement) | [TBD] | R145,000 | ~957 deaths averted/yr | [TBD] | Brief 1 Opt. 4 |
| Terbufos | Adopt T2 + 24-mo gate | DALRRD, NDoH | [TBD] | [TBD] | ≥50% reduction or auto T3 | Immediate/24-mo review | Brief 2 (Coordination) |
| Financing | Ring-fence pesticide levy | DALRRD/Treasury | – | [TBD] | Sustainable funding | [TBD] | Act 36 amendment |