Date: 27 May 2026

# Webpage 1: Policy Brief Hub: Strengthening Pesticide Poisoning Surveillance and Response

URL: https://bridaybrummer.github.io/D2P_project/posts/policy_brief.html

## The three policy briefs

### 1 · Strengthening Pesticide Poisoning Surveillance

Problem: Only 5% of pesticide poisonings are currently captured by surveillance

Policy question. Should NDoH invest in automated, multi-source surveillance to close the detection gap between NMC, the NHLS laboratory, and the Poisons Information Helpline?

Projected impact: 150 deaths averted/ year for R157 000

### 2 · Closing the Coordination Loop

### Problem statement:

Policy question. Should NDoH and DALRRD mandate a closed-loop coordination workflow so that every NMC notification triggers an investigation that is recorded, every EHP→DALRRD referral is structured, and every DALRRD action is fed back?

Projected impact. ~957 deaths averted/year at scale. For ~R145,000/year,

### 3 · Restricting or Banning Terbufos

### Problem:

Policy question. Should South Africa restrict, or fully ban, terbufos as a registered agricultural pesticide?

Projected impact:. X lives saved at X cost

Shared evidence base

All three briefs usea single shared parameter set (cases per year, CFR, per-case costs, decision-tree probabilities, prevention efficacy η, secondary-case multiplier ρ).

Source files:

- Decision Model — burden, parameters, sensitivity analyses

- Costing Analysis — full cost build-up

- Surveillance Concept Note — technical surveillance design

# Webpage 2: Policy Brief 1: Strengthening Pesticide Poisoning Surveillance

Closing the detection gap between NMC, NHLS, and PIH

policy

surveillance

decision-makers

Author

D2P Project Team

Published

September 5, 2025

Modified

May 20, 2026

ImportantFor Decision-Makers

Target audience: Ministerial Advisory Committee (MAC), National Department of Health (NDoH), Provincial Health Leadership, NICD/NHLS leadership.

Companion briefs: Coordination · Terbufos restriction.

## 1. Policy question

Should NDoH invest in automated, multi-source pesticide-poisoning surveillance to close the detection gap between the NMC, NHLS laboratory, and PIH data streams?

## 2. Public health problem

South Africa under-detects pesticide poisoning. Three data streams each see a fraction of the problem; none sees the whole:

- Most cases never appear in NMC.

- Severe laboratory results do not trigger a public-health alert.

- The country’s largest single source of clinical signal — the Poisons Information Helpline — is not used for surveillance.

## 3. Status quo

NoteCanonical model parameters (auto-loaded from the Parameters Hub)

NoteHealth-sector share of the burden — what surveillance unlocks

The public health system bears ~R80M of the R2.34B annual burden on its own budget lines (~R70M NDoH ward/ICU/ventilation/antidote; ~R10M NHLS BChE + confirmatory). Surveillance is a necessary but not sufficient input to reducing that burden — it changes only what is seen. Burden reduction comes from the coordinated response (source removal, regulatory action, clinical management) covered in the Coordination and Terbufos briefs. This brief therefore measures the proportion of true burden detected (P_detect); it does not measure cases or deaths averted.

Architecturally, the three streams are unlinked:

NHLS

NMC notification

monthly extract

✓ MOU feed
operational

BChE monthly

x Not available for
live-patient surveillance

No minimum viable
dataset defined

Healthcare Facility
Clinician / PHO

NDoH / NMC
NDoH-owned
Source of truth

BChE Assay
1,779 severe/year
10,626 tests 2023
Live patients

Chemical Toxicology
Post-mortem only —
not yet done on
live patients

NHLS CDW

NICD SDW

PIH Consultation
~1,158 clinician calls/yr
No minimum dataset

Figure 1: Current surveillance architecture. NMC is NDoH-owned and has demonstrated flexibility and resilience as a national surveillance platform. NHLS BChE results can be routed to NMC via NHLS CDW → NICD SDW (this feed already exists for infectious disease). Two active gaps remain: PIH consultations are not linked to NMC, with neither stream holding a complete minimum dataset for surveillance; forensic chemical toxicology is post-mortem only and fully de-identified (not fit for surveillance linkage in its current form; MLDI system development is a potential future pathway).

What this means in plain numbers.

- NMC notifications: 1,013 (n_nmc_annual)

- NHLS severe BChE inhibitions: 1,779 (n_nhls_severe_annual) out of 10,626 BChE tests (n_nhls_total_annual)

- PIH clinician-initiated calls: 1,158 (n_pih_annual)

- Implied true annual burden:  (n_true_burden_from_statssa_mid)

NMC alone captures  (d_status_quo), i.e. < 5 %.

CautionCaveat: this denominator rests on a CFR assumption

### Detection vs. true burden — a critical distinction

Better surveillance has two opposite numerical effects that decision-makers must not confuse:

| Effect | Direction | Driver | Interpretation |
| --- | --- | --- | --- |
| Observed burden | ↑ | Better case-finding (auto-notify, MVD ingest) | The headline “case count” will rise as detection improves — this is success, not failure. |
| True burden | ↓ | Faster source removal, targeted regulation, prevention | Future poisoning cases and clusters are averted. |

Once the integrated streams are live, reported case counts will rise as detection improves and historical burden estimates should be re-calibrated against the expanded data. This is a surveillance artefact, not a true increase in poisonings, and must be communicated as such in any public reporting.

## 4. Root cause analysis

Surveillance under-detection

NHLS–NMC MOU not
IT-implemented

PIH data not used
for surveillance

Delayed manual reporting

No live-patient
chemical toxicology

✓ NHLS→NMC IT feed
Completed

Option 2: PIH MVD
+ dashboard

Option 1: BChE
auto-notify capability exists

Option 5: Sentinel
toxicology + auto-notify

Figure 2: Root causes of surveillance under-detection and the surveillance-improvement options that address each one.

Three active root causes remain executional, not legislative, and are each already legally permissible under Section 90 of the National Health Act (2003) and the existing NMC regulations. The fourth root cause (NHLS–NMC IT connectivity) has been resolved — the LIS-to-NMC feed is operational, though a severity-threshold rules engine still needs to be configured to enable automated alerting.

## 5. Policy options

Tip✓ NHLS–NMC IT feed — now operational

The NHLS–NICD LIS-to-NMC connector is operational; daily BChE data flows to NICD under the existing MOU. The three active options below build on this.

Reading guide — option numbering. Options below are numbered 1–5 in narrative build order. Backend parameter codes in the CSV (c_S1_*, c_S2_*, c_S1b_*, c_option6_*) are stable identifiers that pre-date the renumbering and do not follow the brief’s order. Cross-walk:

| Option (display) | Description | CSV parameter family |
| --- | --- | --- |
| Option 1 | BChE auto-notification (first build, ★ recommended) | c_S2_BChE_autonotify_* |
| Option 2 | PIH dashboard + MVD (second build, ★ recommended — completes the MVP) | c_S1_PIH_MVD_* |
| Option 3 | Community layer (Phase 2, conditional) | c_S1b_* |
| Option 4 | NMC CIF + agricultural extension (bridge to coordination) | (no dedicated parameter) |
| Option 5 | Sentinel live-patient toxicology (research-funded, distinct purpose) | c_option6_* |

S0 (NHLS→NMC IT feed) is operational and in the baseline. Surveillance MVP = Options 1 + 2.

NoteAudit trail — mini-budget backing the S0 operating cost (R60,000/yr, now in baseline)

### Option 1 — BChE auto-notification (★ recommended — first build, capability exists)

Configure the NHLS LIS to fire an automatic NICD notification when a BChE result shows severe inhibition (< 10 % of normal)*, within 24 hours of validation. No new test, no new reagent contract — only an IT configuration on top of the ~10,626 BChE tests/year already performed (1,779 severe in 2023). Detection rises to ~13 % of true cases (up from ~5 %) for a one-off setup of R200,000, then R55,000/year from Year 2 (Year 1 total: R255,000), deliverable in 2–4 weeks. Uses existing NHLS infrastructure with a single owner (NHLS LIS) and delivers the largest single-option P_detect uplift (+8.5 pp) — recommended as the first build.

- Severe inhibition is most closely related to severe sequelae such as hospitalisation and death [Chaudhary S, Jain N, Atam V, Agarwal A, Singh K, Sawlani K, et al. Prognostic significance of estimation of pseudocholinesterase activity and role of pralidoxime therapy in organophosphorous poisoning. Toxicol Int. 2013;20(3):214]. Taking any BChE test will likely increase the FP rate and this will not be accounted for.

NoteAudit trail — mini-budget backing Option 1 (BChE auto-notify): R55,000/yr

### Option 2 — PIH live dashboard + Minimum Viable Dataset (★ recommended — second build, completes the MVP)

Two layers:

- Short term (1–2 weeks): PIH publishes a live dashboard of pesticide-related calls (counts, geography, agent, severity, demographics, AfriTox agent name). No new data; just a daily extract from existing call records.

- Medium term (3–9 months): PIH and NICD agree a Minimum Viable Dataset (MVD) so the ~1,158 clinician-initiated calls/year can be ingested into NMC as a structured surveillance stream. Agent-name capture is a mandatory MVD field — both PIH and NMC must record the AfriTox product name for every case. To make this reciprocal, NMC should add a structured agent drop-down (pesticide class → active ingredient → AfriTox product name) to its NDoH-hosted notification form: PIH records what the caller reports; NMC records what the clinician confirms. Combined: agent-attribution signal system-wide at near-zero marginal cost.

Detection rises to ~10 % of true cases (up from ~5 %) for a one-off setup of R40,000, then R82,000/year from Year 2 (Year 1 total: R122,000; includes AfriTox agent-name harmonisation). The dashboard ships in days; the MVD ingest is the second build to complete the MVP.

NoteAudit trail — mini-budget backing Option 2 (PIH dashboard + MVD): R82,000/yr

### Option 3 — Community layer (Phase 2) (commission after MVP pilot if rural/informal gap confirms)

Options 1 and 2 improve detection within the formal healthcare system (PIH, NHLS BChE, NMC-notified facilities). They cannot reach cases that never arrive at a formal facility — the child taken to a traditional healer after ingesting street-sold granules, the farm worker who doesn’t present at all, the informal-settlement cluster whose care pathway bypasses formal services.

Important

Pre-condition — non-clinician reporting must be enabled. Option 3 only delivers a coverage uplift if PIH (and the NMC CIF, via Option 4) accept structured reports from non-medical personnel: community health workers (CHWs), environmental health practitioners (EHPs), ward-based outreach teams, agricultural extension officers, teachers, traditional healers, and community members. The Option 2 PIH stream is built on the ~1,158 clinician-initiated PIH calls/year and by construction cannot see cases that never reach a clinician. Without a dedicated non-clinician intake channel — Tier-1 CHW checklist as the structured form, EHP call-back as validation — the CHW network has nowhere to land its reports and Option 3 reduces to training cost with no measurable P_detect gain.

The MVP ceiling (~19% P_detect) is bounded by the reach of formal administrative streams. Option 3 is the mechanism for going beyond it, but only after the MVP has confirmed the remaining gap is structural rather than a compliance issue within the formal system.

Trigger condition. Commission Option 3 if, after 6 months of MVP operation, the geographic distribution of PIH + NHLS + NMC cases shows ≥40% of severe cases originating in districts with low formal-facility access (defined as <1 public hospital per 50km radius). This is a data-driven go/no-go, not a discretionary expansion. CSV parameters: d_S1b_event_community_*, c_S1b_setup_*, c_S1b_op_*, p_fp_S1b_*.

False-positive load and triage architecture. The gross false-positive rate is ~35% (range 20–50%). At P_detect = 0.40 on the mid-burden of 20,960 true cases, the gross notification volume would be ~12,898 events/yr — of which ~8,384 are true cases and ~4,514 are false alerts before filtering. This is solvable with a two-tier triage architecture — the same design used by WHO-EWARN, APSED, and comparable LMIC systems:

- Tier 1 — CHW structured checklist: Community health workers report via a mobile checklist requiring ≥2 of: acute onset, ≥2 affected persons, known or suspected product contact. Events not meeting criteria are logged but no dispatch is triggered.

- Tier 2 — EHP call-back within 24 hours: A provincial EHP calls back to confirm before committing to on-site investigation.

With a two-tier filter, the effective net FP rate drops to approximately 8–12% — within the investigation capacity modelled in the Coordination brief.

Two-stage rollout — Free State and Gauteng first. These two provinces account for an estimated ~50% of the annual pesticide-poisoning burden (working assumption; to be confirmed against the MVP pilot’s geographic distribution from NMC, NHLS, and PIH data). Comparable LMIC systems have achieved P_detect in the range 0.25–0.55 — 1.3–2.9× the MVP ceiling.

| Stage | Provinces | Est. burden share | Setup cost | Operating cost/yr | Go/no-go criterion |
| --- | --- | --- | --- | --- | --- |
| Option 3 pilot | Free State + Gauteng | ~50% | ~R1M | ~R0.8M/yr | Month 12: net P_detect >35% and net FP <15% |
| Option 3 national | All 9 provinces | 100% | ~R3.5M | ~R2.5M/yr | Conditional on pilot outcome |

The cost range (R1M–R3.5M setup; R0.8M–R2.5M/yr operating — approximately 6–18× the MVP operating cost) directly reflects the two-stage choice.

NoteAudit trail — mini-budget backing Option 3 (community layer) operating cost range

### Option 4 — NMC case investigation form + agricultural extension (bridge to coordination)

Surveillance counts cases; investigation captures the source, the product, and the trigger for source removal. The NDoH Guideline for the Investigation of Human Chemical Poisoning (2023) already defines a structured Case Investigation Form (CIF) that EHPs and clinicians are expected to complete within 48 hours of any chemical-poisoning notification — but uptake is inconsistent, the form is not embedded in the NMC workflow, and it lacks interventions that are carried out by DOA (source removal). In addition, occupational exposure (if appropriate) ought to be captured.

This option does two complementary things and is the minimum surveillance-side investment required to make the Coordination response operational:

- Operationalise the existing NDoH CIF inside NMC. Embed the 2023 guideline’s investigation fields as a structured second-stage form auto-triggered by any pesticide-poisoning notification — whether the notification originates from NMC, the Option 2 PIH MVD ingest, or the Option 1 BChE auto-notify rule. EHPs receive a workflow alert; CIF completion within 48 hours becomes a tracked NMC performance indicator (district-level KPI, reported quarterly).

- Add an agricultural-investigation extension module. Additional structured fields layered onto the CIF for:

  - Product origin: formal retail / informal repackaged / agricultural concentrate / unknown;

  - AfriTox-coded agent name (reciprocal with the Option 2 drop-down so PIH-reported and NMC-confirmed agent names are directly comparable);

  - Exposure context: occupational (farm worker, applicator) / dietary / accidental / intentional / pediatric ingestion;

  - Site geolocation (farm GPS / household / market / school) with district code;

  - Source-removal trigger flag — an explicit field that, when set by the EHP, hands the case off to the DALRRD-Act-36 + DoH source-removal workflow described in the Coordination brief.

Cost. ~R45,000 setup (form-template build into the NMC platform; one-day inter-departmental design workshop with NDoH EHP directorate, DALRRD Act-36 registrar, NICD, and PIH) and ~R35,000/yr operating (NICD analyst 0.04 FTE × R650k DPSA L10-11 for form-completion QA, drop-down maintenance and quarterly performance reporting to NDoH). No new headcount — same DPSA L10-11 analyst anchor used for S0, Option 1 and Option 2; no new IT platform — the NMC notification system already supports structured secondary forms.

P_detect impact. Option 4 does not raise the share of true cases entering surveillance — that is the role of Options 1, 2 and 3. Its value is converting detected cases into actionable investigations: the data-quality bridge that lets the coordination response act on the right cases, with the right product information, at the right site. The agent-attribution field from Option 2 records the what; the CIF + agricultural extension records the where, how, and who.

Governance. The form lives inside NMC; build, governance and KPIs are NDoH-owned surveillance infrastructure. The Coordination brief consumes the structured CIF outputs to trigger source removal and inter-departmental escalation. No new legislation required: the CIF exists in the 2023 guideline; Section 90 of the National Health Act and the NMC regulations already authorise the data flows.

### Option 5 — Sentinel live-patient toxicology (★ recommended, medium term — distinct purpose, research-funded)

NHLS currently performs chemical toxicology (qualitative/quantitative pesticide assays) post-mortem only. There is no live-patient toxicology capability. Option 5 funds a sentinel tertiary site (e.g. CHB) to perform live-patient chemical toxicology and/or mass spectometry, scaling to 4–5 sites in phase 2–3. This will only capture ~ 323 severe poisoning cases.

Forensic chemistry is fully de-identified and not fit for surveillance linkage. No patient, facility, or case-linkage identifiers: cannot be matched to NMC or PIH records without structural re-design of specimen accessioning. The MLDI system is the longer-term pathway for surveillance-ready post-mortem toxicology — a separate workstream from Option 5.

Option 5 has a different purpose from Options 1 and 2 and is not a detection-coverage uplift. Options 1 and 2 raise the share of true cases entering surveillance. Option 5 identifies the chemical agents found in severely poisoned living patients at sentinel sites — the missing evidence base for product-specific regulation (see Terbufos brief). Without it, ~10,000 survivors/year are recorded with agent “unknown / suspected” and targeted product restriction has no quantitative footing. Some signal is captured in the SAMRC Injury and Mortality Survey (Prinsloo et al.) (*** NOTE FOR THE AUTHOR ***).

Cost: ~R1.2M pilot site → ~R3.6M for 5-site rollout, 6–12 months. Funded from research-surveillance streams (SAMRC, Bloomberg, Gates), not the surveillance operating budget. Full quantitative concept in the sentinel toxicology appendix.

NoteAudit trail — mini-budget backing Option 5 (sentinel toxicology) costs

### Summary comparison

| Intermediate-outcome costing analysis — surveillance options, base-case. Costs are 2024–25 ZAR; P_detect is the per-case detection probability anchored to the StatsSA MACOD 2023 mid-burden of 20,960 true cases/year. †R / pp = annual operating cost ÷ percentage-point gain in P_detect over status quo. Options 1 and 2 expand coverage within the formal health system. Option 5 is a parallel agent-attribution investment, not a coverage uplift. Option 4 is a data-quality / investigation-form upgrade that converts detected cases into source-removal hand-offs to the Coordination brief; it does not raise P_detect by design. Option 3 is a Phase 2 community layer, commissioned conditional on (i) MVP pilot data confirming a structural rural/informal gap (≥40% of severe cases in low-facility-access districts after 6 months of MVP operation) and (ii) PIH/NMC opening a non-clinician intake channel. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Option | Setup (one-off) | Annual operating (yr 2+) | Year 1 total | P_detect (per-case) | Δ vs. status quo | R / pp† | Time | Parameter |
| Status quo | — | R0 | R0 |  | — | — | — | d_status_quo |
| Option 1 — BChE auto-notify (first build; CSV: c_S2_*) | R200,000 | R55,000 | R255,000 |  | +8.5 pp | R6,471 / pp | 2–4 wks | d_S2_BChE_autonotify |
| Option 2 — PIH dashboard + MVD (+AfriTox agent name) (second build; CSV: c_S1_*) | R40,000 | R82,000 | R122,000 |  | +5.6 pp | R14,643 / pp | 1–2 wks dash / 3–9 mo MVD | d_S1_PIH_MVD |
| Surveillance MVP — Option 1 + Option 2 | R240,000 | R137,000 | R377,000 |  | +14.1 pp | R9,716 / pp | 12 weeks | d_surveillance_mvp |
| Option 3 — Community layer (Phase 2) (pilot: FS + Gauteng; national conditional on pilot; requires PIH/NMC intake from non-clinicians; CSV: c_S1b_*) | R1M–R3.5M | Pilot R0.8M/yr; national R2.5M/yr | R1.8M–R6.0M | 0.25–0.55 (working: 0.40) | +20 to +50 pp | R39,604–R49,801 / pp | 12 mo pilot → national | d_S1b_event_community_mid |
| Option 4 — NMC CIF + agricultural extension (bridge to coordination) | R45,000 | R35,000/yr | R80,000 | n/a (not a coverage uplift) | enables source-removal hand-off | n/a | 4–8 wks | NDoH 2023 CIF guideline |
| Option 5 — Sentinel toxicology (agent attribution — distinct purpose, research-funded; CSV: c_option6_*) | — (incl. in yr 1) | R3.6M/yr (5-site) | R1.2M (1-site pilot) | n/a (not a coverage uplift) | feeds product-banning evidence base | n/a | 6–12 mo pilot | — |

NoteAudit trail — mini-budget backing the R137,000/yr Surveillance MVP operating cost

NoteAudit: parameter names for costing each policy option

Every annual and setup cost in this brief is linked to a row in amua_import_parameters_v4.csv:

| Option | Setup cost parameter | Operating cost parameter |
| --- | --- | --- |
| Option 2 — PIH dashboard + MVD (+ AfriTox harmonisation) | c_S1_PIH_MVD_setup | c_S1_PIH_MVD_op |
| Option 1 — BChE auto-notification | c_S2_BChE_autonotify_setup | c_S2_BChE_autonotify_op |
| Surveillance MVP (Option 1 + Option 2) | c_surv_MVP_setup | c_surv_MVP_op |
| Option 3 — community layer (sensitivity: lo / mid / hi) | c_S1b_setup_mid (lo/hi also exist) | c_S1b_op_mid (lo/hi also exist) |
| S0 — NHLS-NMC IT feed (operational, in baseline) | c_S0_NHLS_NMC_feed_setup | c_S0_NHLS_NMC_feed_op |
| Status quo (NICD program) | — | c_status_quo_program |

Parameter codes (c_S1_*, c_S2_*, c_S1b_*, c_option6_*) pre-date this brief’s narrative reorder — see the cross-walk at the top of §5. Each option’s mini-budget audit trail unpacks the figures into unit-cost and personnel-time components: S0 · Option 1: BChE · Option 2: PIH MVD · MVP (1+2) · Option 3: Community · Option 5: Sentinel. All anchors are DPSA salary scales, NHLS Patterson grades, SITA contracting benchmarks, and AWS af-south-1 pricing — the same anchors as the §7 status-quo build-up. To update a cost: edit the CSV cell and re-render.

## 6. Decision tree — from surveillance investment to detection uplift

NoteAudit trail — how every P_detect value in this brief was derived

None

Option 2 only
R82,000/yr

Option 1 only
R55,000/yr

Option 1 + Option 2
R137,000/yr

Surveillance
investment?

Status quo
P_detect = 0.048
~5% of true cases

+ PIH MVD
P_detect = 0.104
+5.6 pp vs SQ

+ BChE auto-notify
P_detect = 0.133
+8.5 pp vs SQ

Surveillance MVP
P_detect = 0.189
+14.1 pp vs SQ

Option 5 Sentinel toxicology
agent attribution
parallel investment —
see Terbufos brief

Surveillance investment decision tree — per-case detection uplift only. Each option raises P_detect, the share of true annual cases (~20,960 StatsSA-anchored mid-burden) that enter the surveillance system. The absolute burden impact of these uplifts depends on response-side parameters covered in the coordination and terbufos briefs. Option 5 (sentinel toxicology) is shown separately because it is an agent-attribution investment, not a coverage uplift. All numerical values pulled from amua_import_parameters_v4.csv at render time.

The tree reports per-case detection uplift in percentage points. The status-quo node is a measurement of the current detection gap (1,013 NMC notifications ÷ ~20,960 implied true cases), not a baseline from which deaths are counted as averted — surveillance has no response attached. Four detection inputs (d_status_quo, d_S2_BChE_autonotify, d_S1_PIH_MVD, d_surveillance_mvp) and three operating-cost rows (c_S1_PIH_MVD_op, c_S2_BChE_autonotify_op, c_surv_MVP_op) live in amua_import_parameters_v4.csv — edit the CSV and re-render. Option 5 sits outside this tree: it is an agent-attribution investment whose value is parameterised in the Terbufos brief and the sentinel toxicology appendix.

Option 3 (Phase 2 community layer) is not modelled in this decision tree. The MVP arm represents the ceiling achievable by linking existing administrative streams. Option 3 would require a new arm with P_detect drawn from d_S1b_event_community_mid = 0.40 (range 0.25–0.55) and annual operating cost drawn from c_S1b_op_mid = 1,500,000. It is excluded from the current tree because it is a Phase 2 option commissioned conditional on MVP pilot results, not a parallel near-term decision; and because its coordination cost depends on the net false-positive rate after two-tier triage (p_fp_S1b_mid = 0.35 gross; ~8–12% net) modelled in the Coordination brief.

For burden impact, see the next brief. These P_detect figures feed the Coordination brief decision tree, where response efficacy η converts detection into cases averted, and the Terbufos brief, where regulatory restriction converts cases into deaths averted.

## 7. Status-quo costing — what surveillance costs today

NoteHow to read & edit this section

The tables below are the average-cost economic build-up of running surveillance for pesticide poisoning today (status quo, 2024–25 ZAR). They are sourced from an editable workbook — data/surveillance_costing.xlsx — with three sheets:

- personnel — staff time (CTE × FTE %) by stream

- system — infrastructure, hosting, SMS, reagents by stream

- allocation — what share of each stream’s total volume is pesticide-related (e.g. ~100 pesticide notifications/month out of ~10,000 total NMC notifications ≈ 0.84 % of NMC platform OPEX is attributable to pesticide work)

To revise a unit cost or FTE, edit a cell in the .xlsx and re-render — every number below updates. The CSV (amua_import_parameters_v4.csv) remains the source of truth for model parameters and marginal policy-option costs (Option 1 / Option 2 / MVP). Salary anchors come from the DPSA scales (L10–11), NHLS Patterson grades (D/E), DoH OSD scales (MO, pharmacy), NICD recruitment notices and SITA contracting benchmarks; system anchors come from NHLS State Tender RT-262, AWS af-south-1 pricing, Clickatell/BulkSMS SA, and the NICD ICT budget — full citations are in each row’s source column.

- 1. Personnel

- 2. System

- 3. Allocation factors

- 4. Status-quo total

- 5. Marginal cost of policy options

Annual cost-to-employer × FTE share attributable to pesticide surveillance, by stream.

Table 1

|  | Annual CTE (R) | FTE % | Allocated cost (R/yr) | Rationale | Source |
| --- | --- | --- | --- | --- | --- |
| Cross |  |  |  |  |  |
| NICD data engineer (notification feeds) | 750,000 | 10.0% | 75,000 | Maintains NHLS->NMC IT feed (now operational) and BChE auto-notify rules. | SITA / state IT contracting 2024 |
| NICD biostatistician (signal detection) | 850,000 | 5.0% | 42,500 | Spatial-temporal monitoring of pesticide signals across streams. | DPSA L11-12 scale 2024 |
| NMC |  |  |  |  |  |
| NICD epidemiologist (analyst) | 650,000 | 20.0% | 130,000 | 0.2 FTE reviewing/cleaning the ~12k annual NMC notifications; pesticide is ~1% of intake. | DPSA L10-11 scale 2024 + NICD recruitment |
| Provincial communicable-disease coord. | 700,000 | 5.0% | 35,000 | Triage of pesticide-flagged notifications across 9 provinces (cumulative 0.05 FTE). | DoH provincial OSD scale 2024 |
| Clinician notification time | 1,100,000 | 2.0% | 22,000 | ~10 min/notification x ~1,013 notifications/yr ~ 169 hr ~ 1.8% of one MO's year. | DoH MO Grade 1-3 OSD 2024 |
| PIH |  |  |  |  |  |
| Poisons information specialist | 780,000 | 80.0% | 624,000 | Pesticide is ~80% of PIH call volume (12000 of ~16000 clinician-initiated calls). | DoH pharmacy OSD 2024; PIH 2023 report |
| PIH clinical toxicologist (oversight) | 1,300,000 | 5.0% | 65,000 | Senior medical review of complex pesticide consults. | Stellenbosch FoMHS appointment letters |
| Total personnel | — | — | 993,500 | — | — |

Headline read. The status-quo surveillance system already costs roughly R2,833,206/yr in personnel + pesticide-allocated system spend across NMC, PIH, and NHLS BChE — borne almost entirely by NDoH, NHLS, and Stellenbosch FoMHS rather than appearing as a line item. Against that base, the Surveillance MVP (Option 1 + Option 2) adds only R137,000/yr — a 4.8% uplift on current spend for a +14.1 pp jump in P_detect.

## 8. Implementation considerations

| Component | Lead agency | Year-1 cost | Critical path |
| --- | --- | --- | --- |
| Option 2 — PIH dashboard | PIH (Tygerberg) + NICD | 82,000 | Daily extract + hosting; MVD workshop |
| Option 1 — BChE auto-notify | NHLS LIS team | 55,000 | LIS rule configuration; QA review |
| Option 5 — Sentinel toxicology | NHLS clinical chemistry + sentinel hospital | R1,200,000 pilot | Lab method validation; sample logistics |
| Option 3 — Community layer (Phase 2) (pilot: FS + Gauteng; commission after Month 6 MVP review) | NICD + provincial DoH EHPs | Pilot: R1M setup + R0.8M/yr; national: R3.5M setup + R2.5M/yr | CHW two-tier triage training, mobile checklist app, EHP call-back protocol, QA pipeline |

Privacy & legal. The PIH-to-NMC MVD feed transmits personal health information (age-band, sex, geography, clinical data) and must use a secure, authenticated HTTPS/TLS API — no plaintext or email transmission. De-identification before transmission is mandatory (age-band not exact age; province/district not street address; no name or phone number; see Appendix A2). The NHLS BChE auto-notify feed transmits result-level data with patient identifiers to NMC, consistent with the existing NMC notification pathway, and must use the same secure HL7-over-TLS channel. Both flows are POPIA-compliant under existing Section 90 NHA authority. No new legislation required.

Risks. (i) Low BChE testing uptake by clinicians — Option 1 fires only on tests ordered. (ii) Data-quality drift if facility metadata is incomplete. (iii) Capacity bottleneck at provincial response level — the Coordination brief addresses this.

## 9. Recommended next step

Adopt the Surveillance MVP (Option 1 + Option 2) and pilot in 3 provinces (Gauteng, Western Cape, KZN) for 6 months. Approximate pilot budget: ~R137,000 operating (NHLS–NMC IT feed is now operational). Lead agency: NICD as national coordinator.

- Weeks 1–2: Option 2 PIH dashboard live; Option 1 BChE LIS configuration begins.

- Months 1–3: Option 2 MVD workshop with PIH finalised; Option 1 BChE auto-notify QA review completed.

- Month 6: Evaluate against (a) completeness of NHLS severe results in NMC and (b) signal-to-investigation latency.

- Month 9: Add Option 5 sentinel toxicology site, funded from a separate research-surveillance stream.

- Month 12: Review MVP geographic distribution. If ≥40% of severe cases originate in low-facility-access districts, commission the Option 3 Phase 2 pilot (Free State + Gauteng; ~R1M setup + R0.8M/yr operating).

The coordination side — how NICD, EHPs, DALRRD, and provincial response teams act on the improved signal — is in the Coordination brief. The product-specific regulatory action Option 5 makes possible is in the Terbufos brief.

Companion briefs: Coordination · Terbufos restriction · Decision Model · Costing Analysis

Technical appendices: A — Surveillance decision analysis · D — Sentinel toxicology (Option 5 deep dive)

Appendices (this brief): Appendix A — MVD specifications (NMC + PIH)

## Appendix A — Minimum Viable Dataset (MVD) specifications

### A1. NMC MVD — required fields for PIH-to-NMC structured feed

The table below specifies the Minimum Viable Dataset for ingesting PIH clinician-initiated calls into the National Microbiology and Communicable Disease Notification (NMC) system as a structured surveillance stream. These fields must be captured at the point of PIH call (what the caller reports) and confirmed/updated by the notifying clinician (what the clinician confirms). The pesticide-type and circumstances classification is drawn from the existing NMC notification form; the MVD mandates their structured capture for every pesticide-poisoning case.

Agent-name capture is mandatory. Both PIH and NMC must record the AfriTox product name for every case. NMC should add a structured agent drop-down (pesticide class → active ingredient → AfriTox product name) to the NDoH-hosted notification form to make this reciprocal with PIH. Cases with agent “unknown” are acceptable (do not exclude), but the field must be present.

Pesticide type (structured drop-down — mandatory)

Table 6: NMC pesticide-type classification. Source: existing NMC notification form. AfriTox product-name lookup linked to each class at data entry.

| Code | Pesticide type | Example active ingredients |
| --- | --- | --- |
| OPC | Organophosphates | Chlorpyrifos, dimethoate, profenofos |
| CAR | Carbamates | Aldicarb, methomyl, carbofuran |
| PYR | Pyrethroids | Cypermethrin, deltamethrin, permethrin |
| PAR | Paraquat & Diquat | Paraquat dichloride, diquat dibromide |
| PHO | Phosphine & Phosphides | Aluminium phosphide, zinc phosphide |
| NEO | Neonicotinoid Insecticides | Imidacloprid, thiamethoxam |
| ORG | Organochlorines | DDT, endosulfan, lindane |
| CPH | Chlorophenoxy Herbicides | 2,4-D, MCPA, triclopyr |
| GLY | Glyphosates | Glyphosate-IPA, glyphosate-ammonium |
| COU | Coumarin Rodenticides | Brodifacoum, bromadiolone, chlorophacinone |
| FOR | Formamidines | Amitraz, chlordimeform |
| FUN | Fungicides — Unspecified | — |
| HRB | Herbicides — Unspecified | — |
| INS | Insecticides — Unspecified | — |
| DEE | Diethyl-m-toluamide (DEET) | DEET |
| AFX | Aflatoxin | Aflatoxin B1/B2/G1/G2 |
| NAP | Naphthalene (marbles) | Naphthalene |
| OTH | Other | (free text required) |
| UNK | Unknown | — |

Circumstances / intent (structured drop-down — mandatory)

Table 7: NMC circumstances/intent classification. Source: existing NMC notification form. Must be captured at both PIH call (caller-reported) and NMC notification (clinician-confirmed); these may differ and both values should be retained.

| Code | Circumstance | ICD-10 intent mapping |
| --- | --- | --- |
| UI-OCC | Unintentional — Occupational | X48 (farm, pest control, industrial) |
| UI-DOM | Unintentional — Domestic | X40–X44 |
| INT-SH | Intentional — Self-harm | X60–X69 |
| INT-AH | Intentional — Assault/Homicide | X85–X90 |
| ENV-DR | Environmental / Drift | X48 (environmental context) |
| ACC-CN | Accidental contamination (food/water) | X49 |
| UNK-UI | Unknown / Under investigation | — |

Remaining mandatory MVD fields for NMC notification

Table 8: MVD — additional mandatory fields. These are the minimum set required to (a) link across streams, (b) support geographic clustering, and (c) support product-specific attribution. Fields marked “unknown” are acceptable; empty/null is not.

| Field | Format | Notes |
| --- | --- | --- |
| Case date (date of exposure / presentation) | ISO 8601 (YYYY-MM-DD) | Date of poisoning event or first clinical presentation |
| Facility / point of care | Facility NHIS code | Or “PIH referral” if never attended facility |
| Province | 2-letter code (e.g. WC, GP, FS) | Province of exposure, not of facility |
| District | LIM-code or free text | For geographic clustering analysis |
| Outcome at notification | Survived / Died / Unknown | MUST be updated if outcome changes |
| AfriTox product name | Free text + drop-down lookup | Mandatory field; “unknown” is valid if product unidentified |
| Notification source | NMC-direct / PIH-MVD / NHLS-autonotify | Tracks which stream generated the case |

### A2. PIH MVD — required fields including demographic variables

PIH captures call data in its existing Toxicology Management System (TMS). The following fields must be structured (coded, not free-text) in the PIH-to-NMC MVD feed to ensure the data are surveillance-ready. Demographic variables are mandatory — they are the primary tool for detecting vulnerable sub-populations (occupational exposure in farm workers, paediatric accidental ingestion, gender asymmetry in intentional self-harm) and for geographic clustering.

Table 9: PIH MVD — full field specification including demographic variables. Demographic fields (age, sex, caller type, occupation) are mandatory for all calls; a structured unknown code is required if data are not available — blank fields will be rejected in the NMC ingest pipeline.

| Domain | Field | Format | Rationale |
| --- | --- | --- | --- |
| Demographics | Age | Integer (years) or age-band (0–4, 5–14, 15–24, 25–34, 35–49, 50–64, ≥65) | Paediatric vs. adult exposure patterns differ; required for burden modelling |
| Demographics | Sex | M / F / Unknown | Gender asymmetry in intentional self-harm is a known signal |
| Demographics | Caller type | Patient / Clinician / Caregiver / Other | Distinguishes clinician-initiated (surveillance-relevant) from lay calls |
| Demographics | Occupation (if stated) | Free text + coded: farm worker / pesticide applicator / domestic worker / child / other / unknown | Occupational exposure is systematically under-identified |
| Geography | Province of caller | 2-letter code | Derived from caller area code or stated by caller |
| Geography | District (if known) | LIM-code or free text | Optional but captures rural/urban signal |
| Exposure | Pesticide type | NMC drop-down (see A1) | Must align with NMC classification for linkage |
| Exposure | AfriTox product name | Free text + drop-down lookup | Mandatory; “unknown” valid |
| Exposure | Route | Ingestion / Dermal / Inhalation / Ocular / Unknown | Route influences clinical management and surveillance signal |
| Circumstances | Intent | NMC circumstance codes (see A1) | Caller-reported; may be updated by treating clinician |
| Clinical | Severity (caller-assessed) | Mild / Moderate / Severe / Unknown | PSS (Poisoning Severity Score) if TMS supports it |
| Clinical | Referred to facility | Yes / No / Unknown | Links call record to potential NMC notification |
| Linkage | NMC notification number | Free text (if referred and notified) | Enables de-duplicated case linking across PIH + NMC streams |
| System | Call date and time | ISO 8601 (YYYY-MM-DDTHH:MM) | Required for temporal clustering and latency audit |
| System | TMS call ID | Alphanumeric | Internal identifier; retained for audit; not transmitted externally |

POPIA compliance and secure transmission. All PIH-to-NMC transmissions must be de-identified before transmission: no name, phone number, or exact address. Age-band (not exact age), province/district (not street address), and anonymised TMS call ID are sufficient for surveillance linkage and comply with Section 90 of the National Health Act (2003) and POPIA. Exact age may be retained internally within PIH TMS for clinical purposes and transmitted as age-band only.

De-identified health data still constitutes personal information under POPIA. The PIH-to-NMC feed must be implemented as a secure HTTPS/TLS API with mutual authentication (client certificate or token-based) between the PIH TMS and the NMC ingest endpoint. Transmission over email, FTP, or unencrypted HTTP is not acceptable. The MVD ingest pipeline (line item 4 in the Option 2 operating cost) includes the cost of maintaining this secure channel; the one-off setup cost (c_S1_PIH_MVD_setup = R40,000) must include API security configuration and penetration testing as a go-live requirement.

AfriTox agent-name harmonisation. Both PIH (TMS) and NMC (notification form) must use the same AfriTox product-name controlled vocabulary so product-level attribution is consistent across streams. The Option 2 MVD workshop (Months 1–3) should produce a shared AfriTox lookup table embedded in both systems — a single workshop yields cross-stream agent attribution at scale.